## Project Planner
NEWYORK RESTAURANT INSPECTION
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Define Project Objectives and scope. | 1 | 5 |  |  | 0%
Set up the necessary development environment (Python, libraries) | 6 | 3 |  |  | 0%
Load the dataset into a pandas DataFrame | 9 | 4 |  |  | 0%
Explore the dataset's structure, columns, and data types | 13 | 5 |  |  | 0%
Check for missing values and handle them as needed | 18 | 4 |  |  | 0%
Gain a comprehensive understanding of the data's content | 22 | 2 |  |  | 0%
Select a 12-month period for analysis | 24 | 2 |  |  | 0%
Filter the data based on the selected time period | 26 | 5 |  |  | 0%
Clean and preprocess data for subsequent analyses | 31 | 3 |  |  | 0%
Group data by borough and violation type | 34 | 2 |  |  | 0%
Generate visualizations (count plot) to show violation distribution by borough | 36 | 3 |  |  | 0%
Allow user input for keyword selection | 39 | 1 |  |  | 0%
Filter data to retrieve violations containing the user-entered keyword | 40 | 1 |  |  | 0%
Display keyword-related violations and borough distribution | 41 | 1 |  |  | 0%
Identify and filter animal-related violations (e.g., rat, mice) | 42 | 1 |  |  | 0%
Create a time-based trend analysis of these violations | 43 | 2 |  |  | 0%
Generate a line plot to visualize the trend over the 12-month period | 45 | 1 |  |  | 0%
Plot a histogram to show the distribution of inspection scores | 46 | 1 |  |  | 0%
Calculate and visualize the average inspection score for each month | 47 | 2 |  |  | 0%
Examine the potential factors contributing to score fluctuations | 49 | 2 |  |  | 0%
Categorize violations into severity levels | 51 | 1 |  |  | 0%
Calculate average inspection scores for each severity category | 52 | 1 |  |  | 0%
Visualize the relationship between violation severity and inspection scores | 53 | 2 |  |  | 0%
Summarize key findings and insights from each analysis | 55 | 1 |  |  | 0%
Compile visualizations and descriptions into a cohesive report | 57 | 2 |  |  | 0%
Write an abstract and executive summary to provide an overview of the analysis | 59 | 1 |  |  | 0%
Create a visually appealing presentation of the analysis results | 60 | 2 |  |  | 0%
Present the findings to stakeholders, explaining insights and recommendations | 62 | 1 |  |  | 0%
Review the analysis, code, and report for accuracy and completeness | 63 | 2 |  |  | 0%
Iterate on any necessary improvements based on feedback | 65 | 1 |  |  | 0%
Finalize the analysis report, incorporating revisions | 66 | 1 |  |  | 0%
Share the report and presentation with relevant stakeholders | 68 | 1 |  |  | 0%
0%
0%
0%